## Transportation Readiness
Each Category Below will have a detailed Workplan | Task | Start Date | End Date | Task Owner | Status | Comments
Not started, Complete, In process
LICENSURE, ACCREDITATION, CERTIFICATION Lead: Mario | Office location identified | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Licensed business in RI | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Register as State vendor | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| PUC licensure ? | N/A | 2018-11-01 | Mario | Complete | Broker does not need license
TRANSPORTATION PROGRAM ADMINISTRATION Lead: Jason/Mario | Key management staff in RI | 2018-08-09 | 2018-11-01 | Jason/Mario/Lissa/Marlanea | In process | Under negotiation
| Weekly Status Meetings | 2018-08-09 | 2018-12-31 | Jason/Mario/Lissa/Marlanea | In process
| RI Works consideration | 2018-09-01 | Ongoing | Jason/Mario | Not started
| Unemployment etc | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Encourage M/WBE | 2018-09-01 | Ongoing | Jason/Mario | Not started | DOA oversight in play
| Policy and Procedural Manual | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Implementation Plan | Auth to Proceed (see below) | 2018-09-01 | Jason/Mario | Not started
| Websites, Mobile Applications & Other Innovations | 2018-09-01 | 2018-10-01 | Jason/Mario | Not started
TRANSPORTATION PROGRAM ELIGIBILITY AND PROGRAM ENROLLMENT Lead: NEED | Medicaid Eligible and Enrolled Recipients | TBD | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Temporary Assistance for Needy Families (TANF) | TBD | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started | Potential DHS removal of program from brokerage
| Non-Medicaid Elderly Population | TBD | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Process Denial of Service Determinations | TBD | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
RECIPIENT ENROLLMENT AND DISENROLLMENT Lead: NEED | Elderly Transportation Program | 2018-09-01 | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Eligibility Procedures | 2018-09-01 | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Eligibility Verification | 2018-09-01 | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Receive eligibility file from EOHHS | 2018-09-01 | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Challenging member behavior policy and procedure | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Attendant (escort) policy | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Stakeholder education | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Disenrollment policy and procedure | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
LEVELS OF SERVICE AND MODES OF TRAVEL Lead: Mario | Curb-to-Curb Service | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Door to Door Service | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Services available 24/7, 365 days a year. | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Public Transit (bus) | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Limited public vehicle (sedan) | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Ride-Share Program (Uber/Lyft) | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Public Motor Vehicle | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Multi-Passenger Van | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Wheelchair Van | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Ambulance (stretcher van, ALS/BLS) | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Mileage Reimbursement | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
COORDINATION OTHER HEALTH/ SOCIAL SERVICES AVAILABLE TO RECIPIENTS Lead: Jason/Mario | Managed Care Organizations | Auth to Proceed | 12/1/18 | Jason/Mario | Not started
| Accountable Entities | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| RI Public Transit Authority | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
TRANSPORTATION PROVIDER NETWORKS Lead: Jason/Mario | TP supply adequacy | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| TPs insured | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| TPs licensed, certified, permitted | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| TP selection criteria | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| Contingency plans for unexpected peak transportation demands | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Recovery policy | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Incentive program policy and procedure if applicable | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Fraud Waste and Abuse policy | 2018-09-01 | 2018-12-01 | Jason/Mario & Program Integrity | Not started
| Authorizing services | Auth to Proceed | 2018-10-01 | Jason/Mario | Not started
| Scheduling services | Auth to Proceed | 2018-10-01 | Jason/Mario | Not started
| Managing payments | Auth to Proceed | 2018-10-01 | Jason/Mario | Not started
| Making payments | Auth to Proceed | 2018-10-01 | Jason/Mario | Not started
| TP contracts | Auth to Proceed | 2018-11-01 | Jason/Mario & EOHHS Legal | Not started
| TP contracts executed | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| TP monitoring policy and procedures | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Corrective action process | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| TP termination process | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Alternative transportation options | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Post-trip Review and Verification | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Pre trip Review and Trip verification | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Training events and training materials | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Process Retroactive Eligibility Claims | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
TRANSPORTATION PROVIDER AND VEHICLE REQUIREMENTS Lead: Jason/Mario | Vehicle compliance policy | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| AVL capacity | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started | EOHHS granted 90 day grace period from 1/1/19
| ADA compliance | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Permits and licenses | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| TPs located in RI | Auth to Proceed | Ongoing | Jason/Mario | Not started
| Background checks | Auth to Proceed | Ongoing | Jason/Mario | Not started
| TP training curriculum: CPR, HIPAA, Cult Comp, Def Driver | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| TP identification | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
BUSINESS OFFICE AND CALL CENTER LOCATION Lead: Jason/Mario | Co-located in RI | 2018-08-09 | 2018-10-01 | Jason/Mario | In process | Concern with call center reps working from home.
| Staff training curriculum | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Fully staffed | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started | Concern with management presence in RI
| Fully equipped | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
RHP Notices |  |  |  |  | Not started
Not started
Not started
Not started
Not started
Not started
TRANSPORTATION RECIPIENT SERVICES Lead: Jason/Mario | Member materials | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Toll free number(s) | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| 24/7 operations | Auth to Proceed | 2019-01-01 | Jason/Mario | Not started
| Call flow routing | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Telephone Device for the Deaf (TDD) | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Automatic Call Distributor (ACD) | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Call Tracking | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Response standards for member service | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Telephone system back up system | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Determine the Mode of Transport | Auth to Proceed |  | Jason/Mario | Not started
| Call Extraction and Reporting | Auth to Proceed |  | Jason/Mario | Not started
TRANSPORTATION PROVIDER SERVICES Lead: Jason/Mario | Toll free line for provider relations | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Personnel policy | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Response standards for Provider service | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Claims Processing Function | Auth to Proceed | 2018-10-01 | Jason/Mario | Not started
| Prior Authorization | Auth to Proceed | 2018-10-01 | Jason/Mario | Not started
| Provider complaint policy | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Provider Manual | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Process Trip Assignments | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
PAYMENTS Lead: Need | Ability to receive 834 enrollment report | Auth to Proceed | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Receive capitation payments | Auth to Proceed | 2018-11-01 | NEMT Team/Fiscal & IT & Data | Not started
|  | Auth to Proceed | 2018-11-01 | NEMT Team/Fiscal & IT & Data | Not started
| Receive ETP and TANF payments | Auth to Proceed | 2018-11-01 | NEMT Team/Fiscal & IT & Data | Not started
| Fee for service payment receipt | Auth to Proceed | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Claims Processing and MIS | Auth to Proceed | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Audit capacity | Auth to Proceed | 2018-11-01 | NEMT Team/Fiscal | Not started
| Financial Data Reporting | Auth to Proceed | 2018-11-01 | NEMT Team/Fiscal & IT & Data | Not started
| Rate Certification | 2018-08-09 | 2018-09-15 | NEMT Team/Fiscal | In process
GUARANTEES, WARRANTIES, AND CERTIFICATIONS Lead: Mario | Broker Certification of Truthfulness | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Broker Certification of Legality | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Performance Bond or Substitutes | 2018-08-09 | 2018-08-16 | Purchases | Complete
| Subcontracts | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Professional liability insurance | 2018-08-09 | 2018-08-16 | Purchases | Complete
| Workers' compensation | 2018-08-09 | 2018-08-16 | Purchases | Complete
| Comprehensive liability insurance | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Property damage insurance | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Errors and Omissions insurance | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Automobile Liability | 2018-08-09 | 2018-08-16 | Purchases | Complete
PERSONNEL Lead: Jason/Mario | Personnel policy and procedures | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Full staff compliment | 2018-08-09 | 2018-11-01 | Jason/Mario | Not started
| Staff fully trained | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
RECORDS RETENTION Lead: Jason/Mario | Ability to maintain for 10 years | 2018-09-01 | Ongoing | Jason/Mario | Not started
| Service delivery | 2018-09-01 | Ongoing | Jason/Mario | Not started
| Financial statements | 2018-09-01 | Ongoing | Jason/Mario | Not started
PERFORMANCE STANDARDS AND DAMAGES Lead: Jason/Mario | Electronic report submission | 2018-08-09 | 2018-11-01 | Jason/Mario | In process
| 837 submission | 2018-08-09 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| 277CA reports | 2018-08-09 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Encounter data and reporting | Auth to Proceed | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Grievance and Appeals data and reporting | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| Quality Assurance data and reporting | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| Quality Improvement & Operations Plan | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| Recipient Satisfaction Data and reporting | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| Fraud And Abuse reports | Auth to Proceed | 2018-11-01 | NEMT Team/Progrsm Integrity | Not started
| Recovery reporting | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| Utilization Review policy | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Performance reports | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Liquidated Damages | 2018-08-09 | 2018-11-01 | Jason/Mario | In process | EOHHS granted 180 grace period from start of contract.
| Quality Assurance policy | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
| Complaint data and reporting | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
COMPLIANCE Lead: Jason/Mario | Disclosure of Ownership and Control Interest | 2018-09-01 | 2018-12-01 | Jason/Mario | Not started
COMPLAINTS, GRIEVANCE AND APPEALS Lead: Jason/Mario | Complaint Resolution policy | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Grievance Process policy | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Expedited Resolution of Appeals process | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
ANNUAL COMPLIANCE AUDIT Lead: Jason/Mario | Audit compliance per contract | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
INSPECTION OF WORK PERFORMED Lead: Jason/Mario | Marketing materials | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Written materials | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Recipient Communication | 2018-09-01 | 2018-11-01 | Jason/Mario | Not started
| Partner/Stakeholder Communication/Engagement | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
| Multilingual capacity | 2018-10-01 | 2018-11-01 | Jason/Mario | Not started
| Maintain Confidential Information | 2018-10-01 | 2018-11-01 | Jason/Mario | Not started
| T/P subcontracts | Auth to Proceed | 2018-11-01 | Jason/Mario | Not started
Not started
OTHER CONTRACT TERMS AND CONDITIONS Lead: Jason/Mario | Conflict of Interest | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Reporting of Political Contributions | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Environmental Tobacco Smoke | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
| Other workplace federal requirements | Auth to Proceed | 2018-12-01 | Jason/Mario | Not started
Auth to Proceed = | Activity to begin upon EOHHS' receipt of an Authorization to Proceed letter from Purchases to allow bidder to proceed with certain tasks prior to issue of Purchase Order.