## Transportation Readiness
Each Category Below will have a detailed Workplan | Task | Start Date | End Date | Task Owner | Status | Comments
Not started, Complete, In process
LICENSURE, ACCREDITATION, CERTIFICATION Lead: Mario | Office location identified | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Licensed business in RI | 2018-09-01 | 2018-11-01 | Jason/Mario | Complete
| Register as State vendor | 2018-09-01 | 2018-11-01 | Jason/Mario | Complete
| PUC licensure ? | N/A | 2018-11-01 | Mario | Complete | Broker does not need license
TRANSPORTATION PROGRAM ADMINISTRATION Lead: Jason/Mario | Key management staff in RI | 2018-08-09 | 2018-11-01 | Jason/Mario/Lissa/Marlanea | In process | Under negotiation
| Weekly Status Meetings | 2018-08-09 | 2018-12-31 | Jason/Mario/Lissa/Marlanea | In process
| RI Works consideration | Signed contract | Ongoing | Jason/Mario | In process | Lissa to touch base with Kim Rauch
| Unemployment etc | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Encourage M/WBE | Signed contract | Ongoing | Jason/Mario | Not started | DOA oversight in play
| Policy and Procedural Manual | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Implementation Plan | TBD | 2018-09-01 | Jason/Mario | Not started
| Websites, Mobile Applications & Other Innovations | Signed contract | Ongoing | Jason/Mario | Not started
TRANSPORTATION PROGRAM ELIGIBILITY AND PROGRAM ENROLLMENT Lead: NEED | Medicaid Eligible and Enrolled Recipients | TBD | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Temporary Assistance for Needy Families (TANF) | TBD | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started | Potential DHS removal of program from brokerage
| Non-Medicaid Elderly Population | TBD | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Process Denial of Service Determinations | TBD | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
RECIPIENT ENROLLMENT AND DISENROLLMENT Lead: NEED | Elderly Transportation Program | Signed contract | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Eligibility Procedures | Signed contract | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Eligibility Verification | Signed contract | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Receive eligibility file from EOHHS | Signed contract | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Challenging member behavior policy and procedure | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Attendant (escort) policy | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Stakeholder education | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Disenrollment policy and procedure | Signed contract | 2018-11-01 | Jason/Mario | Not started
LEVELS OF SERVICE AND MODES OF TRAVEL Lead: Mario | Curb-to-Curb Service | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Door to Door Service | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Services available 24/7, 365 days a year. | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Public Transit (bus) | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Limited public vehicle (sedan) | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Ride-Share Program (Uber/Lyft) | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Public Motor Vehicle | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Multi-Passenger Van | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Wheelchair Van | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Ambulance (stretcher van, ALS/BLS) | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Mileage Reimbursement | Signed contract | 2018-11-01 | Jason/Mario | Not started
COORDINATION OTHER HEALTH/ SOCIAL SERVICES AVAILABLE TO RECIPIENTS Lead: Jason/Mario | Managed Care Organizations | Signed contract | 12/1/18 | Jason/Mario | Not started
| Accountable Entities | Signed contract | 2018-12-01 | Jason/Mario | Not started
| RI Public Transit Authority | Signed contract | 2018-12-01 | Jason/Mario | Not started
TRANSPORTATION PROVIDER NETWORKS Lead: Jason/Mario | TP supply adequacy | Signed contract | 2018-11-01 | Jason/Mario | Not started
| TPs insured | Signed contract | 2018-11-01 | Jason/Mario | Not started
| TPs licensed, certified, permitted | Signed contract | 2018-11-01 | Jason/Mario | Not started
| TP selection criteria | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Contingency plans for unexpected peak transportation demands | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Recovery policy | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Incentive program policy and procedure if applicable | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Fraud Waste and Abuse policy | Signed contract | 2018-12-01 | Jason/Mario & Program Integrity | Not started
| Authorizing services | Signed contract | 2018-10-01 | Jason/Mario | Not started
| Scheduling services | Signed contract | 2018-10-01 | Jason/Mario | Not started
| Managing payments | Signed contract | 2018-10-01 | Jason/Mario | Not started
| Making payments | Signed contract | 2018-10-01 | Jason/Mario | Not started
| TP contracts | Signed contract | 2018-11-01 | Jason/Mario & EOHHS Legal | Not started
| TP contracts executed | Signed contract | 2018-11-01 | Jason/Mario | Not started
| TP monitoring policy and procedures | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Corrective action process | Signed contract | 2018-12-01 | Jason/Mario | Not started
| TP termination process | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Alternative transportation options | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Post-trip Review and Verification | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Pre trip Review and Trip verification | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Training events and training materials | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Process Retroactive Eligibility Claims | Signed contract | 2018-11-01 | Jason/Mario | Not started
TRANSPORTATION PROVIDER AND VEHICLE REQUIREMENTS Lead: Jason/Mario | Vehicle compliance policy | Signed contract | 2018-11-01 | Jason/Mario | Not started
| AVL capacity | Signed contract | 2018-11-01 | Jason/Mario | Not started | EOHHS granted 90 day grace period from 1/1/19
| ADA compliance | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Permits and licenses | Signed contract | 2018-11-01 | Jason/Mario | Not started
| TPs located in RI | Signed contract | Ongoing | Jason/Mario | Not started
| Background checks | Signed contract | Ongoing | Jason/Mario | Not started
| TP training curriculum: CPR, HIPAA, Cult Comp, Def Driver | Signed contract | 2018-11-01 | Jason/Mario | Not started
| TP identification | Signed contract | 2018-12-01 | Jason/Mario | Not started
BUSINESS OFFICE AND CALL CENTER LOCATION Lead: Jason/Mario | Co-located in RI | 2018-08-09 | 2018-10-01 | Jason/Mario | In process | Concern with call center reps working from home.
| Staff training curriculum | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Fully staffed | Signed contract | 2018-11-01 | Jason/Mario | Not started | Concern with management presence in RI
| Fully equipped | Signed contract | 2018-11-01 | Jason/Mario | Not started
RHP Notices |  |  |  |  | Not started
Not started
Not started
Not started
Not started
Not started
TRANSPORTATION RECIPIENT SERVICES Lead: Jason/Mario | Member materials | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Toll free number(s) | Signed contract | 2018-12-01 | Jason/Mario | Not started
| 24/7 operations | Signed contract | 2019-01-01 | Jason/Mario | Not started
| Call flow routing | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Telephone Device for the Deaf (TDD) | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Automatic Call Distributor (ACD) | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Call Tracking | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Response standards for member service | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Telephone system back up system | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Determine the Mode of Transport | Signed contract |  | Jason/Mario | Not started
| Call Extraction and Reporting | Signed contract |  | Jason/Mario | Not started
TRANSPORTATION PROVIDER SERVICES Lead: Jason/Mario | Toll free line for provider relations | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Personnel policy | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Response standards for Provider service | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Claims Processing Function | Signed contract | 2018-10-01 | Jason/Mario | Not started
| Prior Authorization | Signed contract | 2018-10-01 | Jason/Mario | Not started
| Provider complaint policy | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Provider Manual | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Process Trip Assignments | Signed contract | 2018-11-01 | Jason/Mario | Not started
PAYMENTS Lead: Need | Ability to receive 834 enrollment report | Signed contract | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Receive capitation payments | Signed contract | 2018-11-01 | NEMT Team/Fiscal & IT & Data | Not started
|  | Signed contract | 2018-11-01 | NEMT Team/Fiscal & IT & Data | Not started
| Receive ETP and TANF payments | Signed contract | 2018-11-01 | NEMT Team/Fiscal & IT & Data | Not started
| Fee for service payment receipt | Signed contract | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Claims Processing and MIS | Signed contract | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Audit capacity | Signed contract | 2018-11-01 | NEMT Team/Fiscal | Not started
| Financial Data Reporting | Signed contract | 2018-11-01 | NEMT Team/Fiscal & IT & Data | Not started
| Rate Certification | 2018-08-09 | 2018-09-15 | NEMT Team/Fiscal | Complete | Not necessary
GUARANTEES, WARRANTIES, AND CERTIFICATIONS Lead: Mario | Broker Certification of Truthfulness | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Broker Certification of Legality | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Insurance endorsement | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Performance Bond or Substitutes | 2018-08-09 | 2018-08-16 | Purchases | Complete
| Subcontracts | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Professional liability insurance | 2018-08-09 | 2018-08-16 | Purchases | Complete
| Workers' compensation | 2018-08-09 | 2018-08-16 | Purchases | Complete
| Comprehensive liability insurance | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Property damage insurance | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Errors and Omissions insurance | 2018-08-09 | 2018-12-01 | Jason/Mario | In process
| Automobile Liability | 2018-08-09 | 2018-08-16 | Purchases | Complete
PERSONNEL Lead: Jason/Mario | Personnel policy and procedures | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Full staff compliment | 2018-08-09 | 2018-11-01 | Jason/Mario | In process
| Staff fully trained | Signed contract | 2018-12-01 | Jason/Mario | Not started
RECORDS RETENTION Lead: Jason/Mario | Ability to maintain for 10 years | Signed contract | Ongoing | Jason/Mario | Not started
| Service delivery | Signed contract | Ongoing | Jason/Mario | Not started
| Financial statements | Signed contract | Ongoing | Jason/Mario | Not started
PERFORMANCE STANDARDS AND DAMAGES Lead: Jason/Mario | Electronic report submission | 2018-08-09 | 2018-11-01 | Jason/Mario | In process
| 837 submission | 2018-08-09 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| 277CA reports | 2018-08-09 | 2018-11-01 | NEMT Team/EOHHS IT & Data | In process
| Encounter data and reporting | Signed contract | 2018-11-01 | NEMT Team/EOHHS IT & Data | Not started
| Grievance and Appeals data and reporting | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Quality Assurance data and reporting | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Quality Improvement & Operations Plan | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Recipient Satisfaction Data and reporting | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Fraud And Abuse reports | Signed contract | 2018-11-01 | NEMT Team/Progrsm Integrity | Not started
| Recovery reporting | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Utilization Review policy | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Performance reports | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Liquidated Damages | 2018-08-09 | 2018-11-01 | Jason/Mario | In process | EOHHS granted 180 grace period from start of contract.
| Quality Assurance policy | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Complaint data and reporting | Signed contract | 2018-12-01 | Jason/Mario | Not started
COMPLIANCE Lead: Jason/Mario | Disclosure of Ownership and Control Interest | Signed contract | 2018-12-01 | Jason/Mario | Not started
COMPLAINTS, GRIEVANCE AND APPEALS Lead: Jason/Mario | Complaint Resolution policy | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Grievance Process policy | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Expedited Resolution of Appeals process | Signed contract | 2018-11-01 | Jason/Mario | Not started
ANNUAL COMPLIANCE AUDIT Lead: Jason/Mario | Audit compliance per contract | Signed contract | 2018-11-01 | Jason/Mario | Not started
INSPECTION OF WORK PERFORMED Lead: Jason/Mario | Marketing materials | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Written materials | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Recipient Communication | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Partner/Stakeholder Communication/Engagement | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Multilingual capacity | Signed contract | 2018-11-01 | Jason/Mario | Not started
| Maintain Confidential Information | Signed contract | 2018-11-01 | Jason/Mario | Not started
| T/P subcontracts | Signed contract | 2018-11-01 | Jason/Mario | Not started
Not started
OTHER CONTRACT TERMS AND CONDITIONS Lead: Jason/Mario | Conflict of Interest | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Reporting of Political Contributions | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Environmental Tobacco Smoke | Signed contract | 2018-12-01 | Jason/Mario | Not started
| Other workplace federal requirements | Signed contract | 2018-12-01 | Jason/Mario | Not started