## Project Status Update
Transportation Transition | [16 empty] | Project Manager: |  |  |  |  | Matt Kiehnle
[17 empty] | Today's Date: |  |  |  |  | 2019-02-26
Project Status Update | [16 empty] | Overall Project Status: |  |  |  |  | At Risk
Category |  |  | Status |  | Project Manager's Notes
Action Items |  |  | At Risk |  | 1. MTM to provide finalized updated implementation reporting 1/25 at 3PM 2. Monitoring of MTM actions towards CAP 3. Decision points around MTM progress/performance as necessary.
Schedule |  |  | At Risk
Risks |  |  | At Risk |  | Template of perferred reporting sent to MTM, waiting for response from Paul on Friday. Current reporting is useable if necessary but not the clearest to be able to easily see correlation between provider, driver, vehichle credentialing MTM needs to provide continued updates of remaining credentialing efforts for Phase 2 of the credentialing processes that is due by 2/1. This needs to be reported in a clear and consistent manner that meets EOHHS needs to evaluate status
Issues |  |  | On Track
Misc. |  |  | On Track
Anticipated vs. Actual Rate of Completion as of Today (Overall % and Task Count)
Start Date: |  |  | 2018-08-01 |  |  |  | Goal Completion Date: |  |  |  | 2018-12-31 |  |  |  | # Days until Goal Completion Date: | [8 empty] | -57
Risks | [5 empty] | Issues | [6 empty] | Questions | [6 empty] | Decisions
Unresolved |  |  | Resolved |  |  | Unresolved |  |  |  | Resolved |  |  | Unresolved |  |  | Resolved |  |  |  | Unresolved |  |  |  | Resolved
0 |  |  | 3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 1 |  |  |  | 0 |  |  |  | 1
Action Items
Total |  | Complete |  | Critical |  |  |  | In Progress |  | Overdue |  | With Vendor |  | Blocked |  |  | Incomplete |  |  | Not Yet Due |  |  | Unknown
139 |  | 139 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
# | Objectives & Deliverables | [17 empty] | O / D | # Related Tasks |  |  |  | Tasks Complete
[24 empty] | # | %
1 | Systems implementation and data transfers (LogistiCare, MTM and EOHHS) | [17 empty] | D | 12 |  |  |  | 12 | 100%
2 | Transportation network adequacy and access | [17 empty] | O | 14 |  |  |  | 14 | 100%
3 | Policies and Procedures, Requirements, Compliance and Reporting | [17 empty] | D | 31 |  |  |  | 31 | 100%
4 | Stakeholder Engagement/Communications | [17 empty] | D | 32 |  |  |  | 32 | 100%
5 | Broker requirements | [17 empty] | O | 22 |  |  |  | 22 | 100%
6 | Operations | [17 empty] | D | 21 |  |  |  | 21 | 100%
7 | EOHHS Financial | [17 empty] | O | 5 |  |  |  | 5 | 100%
8 | Regulations and Policy | [17 empty] | D | 2 |  |  |  | 2 | 100%
Role | [8 empty] | Project Member Name | [8 empty] | Agency |  |  | Decision Rights
EOHHS Deputy Director | [8 empty] | January Angeles | [8 empty] | EOHHS |  |  | Approval Required
Project Lead | [8 empty] | Kristin Sousa | [8 empty] | EOHHS |  |  | Approval Required
Stakeholder Engagement/Systems | [8 empty] | Marlanea Peabody | [8 empty] | EOHHS |  |  | Consulted
Project Manager | [8 empty] | Maria Narishkin | [8 empty] | EOHHS
Transportation Team Lead | [8 empty] | Jason Lyon | [8 empty] | EOHHS
Transportation Team Manager | [8 empty] | Mario Olivieri | [8 empty] | EOHHS
Stakeholder Engagement | [8 empty] | Brenna McCabe and Diana Beaton | [8 empty] | EOHHS
Policy and Compliance | [8 empty] | Meghan Ruane and Ave Houston | [8 empty] | EOHHS
Impact Goal:
Implementation of new vendor contract including readiness and operations for the Medicaid non-emergency Medical Transportation program, the Elderly Transportation Program and transportation for TANF recipients
Opportunity Statement:
Anticipated Risks & Obstacles | [12 empty] | Key Performance Indicators
1 | LGTC not cooperating with transition -LGTC shared documents and transitioned toll free number | [11 empty] | 1
2 | [12 empty] | 2
3 | [12 empty] | 3
4 | [12 empty] | 4
Note on I6: If On Track, What are the most critical action items coming up? If Off Track, what are the the most critical action items to get back on track? If At Risk, what action items must be completed?
Note on I7: Is the project on schedule to hit its targets? If the goal of the "project" is to reach an outcome goal, are the metrics on track? If the project has a defined end point, have action items been completed in a timely manner?
Note on I8: What problems to achieving the project end or metrics may be encountered? What should the project lead focus on mitigating and how should it be done?
Note on I9: What challenges is the project currently facing? How should they be overcome?
Note on I10: What else should the project lead know about progress?
Note on A11: If the project manager is using the action item tab, this graph will automatically update to show actual project progress vs. anticipated project progress.
Note on A14: If the project manager is using the "Risks & Issues" tab, this will automatically update to show resolved and unresolved risks
Note on Q14: If the project manager is using the "Risks & Issues" tab, this will automatically update to show resolved and unresolved issues
Note on AG14: If the project manager is using the "Questions & Decisions" tab, this will automatically update to show resolved and unresolved questions
Note on AW14: If the project manager is using the "Questions & Decisions" tab, this will automatically update to show resolved and unresolved decisions
Note on C20: This part of the project charter should be used to highlight the work that needs to be performed by the team. For example, it could be gathering data and preparing an analysis, developing and evaluation strategy, submitting a budget article. What written work or other concrete deliverable will the project accomplish?
Note on AT20: Objective or Deliverable
Note on AW20: If you are using the "Action Items" tab, include the corresponding objective or deliverable # in each action item, and this section will automatically update.
Note on A30: For each person on the project, why are they on the project? What contribution are they expected to make?
Note on BA30: Who is empowered to make decisions for the project? Who has the power to say yes?
Note on A39: What is the project trying to achieve? When this goal is achieved, the project will be closed (e.g. Launch website, reduce backlog to 10% of total applications, win $1m in grant funding)
Note on A41: Why is this project worth undertaking? What opportunity does the group have to seize?
Note on A43: What does the group see as likely challenges that should be mitigated from the beginning of the project?
Note on AG43: What metrics will the project collect to know if it is being successful? At least some should be collected weekly to know that short term actions are having intended effects.

## Additional PM Notes
Please use this space to report qualitiative updates.
Progress:
New Issues or Stalled Action Items:
Cross-Agency Impact:
[Test text]
Escalations Suggested:
[Test text]

## Action Items
# | Action Item | Reason | Del | Accountable | Support | Origin | Created | Start | Due | Done | Status
1.01 | Send Medicaid Production File | Eligibility | 1 | Marlanea | Steve DXC |  |  | 2018-12-08 | 2018-12-08 | 2018-12-11 | Complete
1.02 | Send TANF Production File | Eligibility | 1 | Marlanea | Steve DXC |  |  | 2018-12-08 | 2018-12-10 | 2018-12-10 | Complete
1.03 | Test enrollment file transfer for Medicaid Eligibility (834) | Eligibility | 1 | Marlanea | Steve DXC |  | 2018-09-26 | 2018-12-01 | 2018-12-05 | 2018-11-25 | Complete
1.04 | Test enrollment file transfer for TANF Eligibility | Eligibility | 1 | Marlanea | Steve DXC - Steve Fugate |  | 2018-09-26 | 2018-12-01 | 2018-12-05 | 2018-11-25 | Complete
1.05 | Review P&P for retroactive eligibility claims processing |  | 1 | Marlanea | Steve Bridges |  | 2018-09-26 | 2018-12-01 | 2018-12-05 |  | Complete
1.06 | Update TANF eligibility files to include dependent information |  | 1 | Marlanea | Steve Bridges/ Deloite |  |  | 2018-12-20 | 2019-01-15 |  | Complete
1.07 | MTM to sent provider files to DXC |  | 1 | Marlanea | Steve DXC |  |  | 2019-01-15 | 2019-04-30 |  | Complete
1.08 | Test and verify broker's ability for 837 Encounter data submission |  | 1 | Marlanea | Steve DXC |  | 2018-09-26 | 2019-04-01 | 2019-04-30 |  | Complete
1.09 | Send test Change file | Eligibility | 1 | Marlanea | Steve DXC |  |  | 2018-12-03 | 2018-12-14 |  | Complete
1.12 | Set up weekly meeting with EOHHS and LGTC |  | 1 | Jason | Mario |  |  | 2018-11-19 | 2018-11-21 | 2018-11-21 | Complete
1.14 | Review MTM's TP Claims processing function |  | 1 | Steve |  |  | 2018-09-26 |  | 2018-12-10 |  | Complete
1.2 | Decide on MTM's request for post trip verification to be done through EOHHS and Medicaid medical claims | Post trip verification | 1 | Marlanea | January Kristin | Ops Meeting | 2018-11-20 | 2019-04-01 | 2019-04-30 | 2018-11-26 | Complete
2.03 | Approve TP contract template |  | 2 | Jason | Mario |  | 2018-09-26 |  | 2018-11-01 | 2018-11-20 | Complete
2.04 | Monitor number and types of TP contracts executed | Network adequacy | 2 | Jason | Mario Ave |  | 2018-09-26 | 2018-11-29 | 2018-11-29 | 2018-11-29 | Complete
2.05 | Monitor and ensure TP supply adequacy | Operations | 2 | Jason | Mario |  | 2018-09-26 | 2018-11-29 | 2018-11-29 |  | Complete
2.06 | Monitor and review GEO access map form MTM | Network adequacy | 2 | Jason | Mario |  | 2018-11-09 | 2018-11-29 | 2018-11-29 | 2018-11-29 | Complete
2.07 | Provide current usage member data from LGTC to MTM | TP Network | 2 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-11-16 | 2018-11-30 | Complete
2.08 | Provide encounter Data to MTM | MTM to use for provider recruitment effort | 2 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-11-16 | 2018-11-20 | Complete
2.09 | ADA Eligibility RIPTA database sharing | Eligibility Verification | 2 | Marlanea | Steve DXC |  | 2018-09-26 |  | 2018-11-30 | 2018-11-27 | Complete
2.1 | Get list of all medical providers from DXC | To provide data to MTM | 2 | Marlanea | Steve DXC Jason |  | 2018-11-09 | 2018-11-14 | 2018-11-16 | 2018-11-27 | Complete
2.11 | Approve continuity of care for mode of transportation plan |  | 2 | Jason | Mario |  |  | 2018-11-15 | 2018-11-30 | 2018-11-29 | Complete
2.12 | Chart TP supply in comparison with LGTC | TP Network | 2 | Mark | Mario |  | 2018-11-30 | 2018-11-30 | 2018-12-15 |  | Complete
2.3 | Review MTM's list of providers from which they acquired standing order information | Standing orders | 2 | Jason | Mario | Ops Meeting | 2018-11-20 | 2018-11-29 | 2018-12-12 |  | Complete
2.31 | Review determination on dialysis center transportation modes review by MTM | Dialysis transport | 2 | Mario | Jason | Ops Meeting | 2018-11-20 | 2018-11-29 | 2018-11-30 |  | Complete
2.32 | Rose and Patrick to meet to discuss proactive communication on MTM vendor change | Access Awareness | 2 | Patrick T | Rose Jones |  | 2018-12-12 | 2018-12-12 | 2018-12-20 |  | Complete
2.33 | Create report of credentialing plane for MTM to share with LVW on 12/21/18 | Access Awareness | 2 | Marlanea | Matt K |  | 2018-12-12 | 2018-12-12 | 2018-12-20 |  | Complete
3.01 | Staffing P&P Review | Contract Compliance | 3 | Jason | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-20 | Complete
3.02 | Review and approve RI Operating Procedure Manual |  | 3 | Meghan Jason | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-12-05 |  | Complete
3.03 | Review FWA policy |  | 3 | Tom Bouchard | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-01 | 2018-11-20 | Complete
3.05 | Review forms for Pre-trip verification |  | 3 | Jason | Ave Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-20 | Complete
3.06 | Review forms for post-trip verification |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2019-04-01 | 2018-11-27 | Complete
3.13 | Review and approve P&P for TP monitoring, corrective action, termination… |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-23 | Complete
3.15 | Review and approve P&P for TP credentialing including background checks, review of CMS's List of Excluded Individuals and the System for Award Management |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-23 | Complete
3.17 | Review and approve staff training curriculum |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-23 | Complete
3.18 | Review and approve Complaint resolution policy |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-23 | Complete
3.22 | Review and approve TP manual |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-20 | Complete
3.27 | Review TP permits, licenses, insurance |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-05 | 2018-11-20 | Complete
3.28 | Review and approve P&P for TP vehicle compliance including PUC license, ADA compliance and vehicle inspection process and forms |  | 3 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-12-07 | 2018-11-20 | Complete
3.32 | Review and approve Quality Assurance Policy |  | 3 |  | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-05 | 2018-11-20 | Complete
3.33 | Verify CCRs' multilingual capacity |  | 3 |  | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
3.35 | Ensure compliance on AVL Capacity for vehicles (Written Attestation) |  | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2019-04-01 | 2019-04-08 | 2018-11-26 | Complete
3.36 | Review proposed report templates and ensure they meet contract requirements | Contract Compliance | 3 | Mark | Mario Meghan |  | 2018-09-26 | 2018-11-21 | 2018-12-13 |  | Complete
3.37 | Review and approve broker marketing materials | Marketing material review | 3 | Brenna | Diana |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-28 | Complete
3.38 | Review and approve written material | Marketing material review | 3 | Meghan | Ave Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-21 | Complete
3.41 | Review TANF Rules |  | 3 | Mario |  |  |  | 2018-11-19 | 2018-11-21 | 2018-11-30 | Complete
3.5 | Review/approve bus letter |  | 3 | Meghan | Ave |  |  | 2018-11-18 | 2018-11-22 | 2018-11-20 | Complete
3.51 | Review/approve Audit recoupment letter |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
3.52 | Review/approve disaster recovery plan |  | 3 | Meghan | Ave |  |  | 2018-11-15 | 2018-11-21 | 2018-11-19 | Complete
3.53 | Review/approve GMR Trip log |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
3.54 | Review/approve incident/accident report form |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
3.54 | Review/approve LON Ambulance |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
3.55 | Review/approve LON Standard |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
3.56 | Review/approve MTM Currency Welcome Letter no public transit GMR Letter |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
3.57 | Review/approve MTM Incoming call guide |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
3.58 | Review/approve MTM Provider Audit |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
3.59 | Review/approve TP Helpdesk |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-21 | Complete
3.6 | Review/approve Generic RFI |  | 3 | Jason | Mario |  |  | 2018-11-01 | 2018-11-15 | 2018-11-20 | Complete
4.01 | Send approved postcard to Medicaid, ETP and TANF members | Stakeholder engagement | 4 | Brenna | Diana Jason Meghan Ave |  | 2018-09-26 | 2018-11-01 | 2018-11-07 |  | Complete
4.03 | Dialysis Meeting | MTM Meet & Greet | 4 | Mario |  |  | 2018-11-09 | 2018-11-07 | 2018-11-07 | 2018-11-07 | Complete
4.04 | Consumer Advisory Committee Meeting | Transition Update | 4 | Marlanea, January, Lissa, Diana |  |  | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | Complete
4.05 | Long Term Care Coordinating Council (LTCCC) Meeting | Transition Update | 4 | Marlanea, Mario, Mike |  |  | 2018-11-09 |  | 2018-11-14 | 2018-11-14 | Complete
4.06 | Substance Use and Leadership Council Meeting | MTM Meet-and-Greet/Overview | 4 | Marlanea, Jason, Mike, Kristin |  |  | 2018-11-09 |  | 2018-11-15 | 2018-11-15 | Complete
4.07 | Assisted Living Providers Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 | 2018-11-30 | 2018-12-07 | 2018-12-07 | Complete
4.08 | Stakeholder/Advocate Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-11-30 | 2018-11-30 | Complete
4.09 | Stakeholder/Advocate Meeting | Transition update | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-20 |  | Complete
4.11 | Internal email to EOHHS, BHDDH, DEA, DHS staff meeting | Transition overview | 4 | Brenna |  |  | 2018-11-09 | 2018-11-09 | 2018-11-27 | 2018-12-03 | Complete
4.12 | Federally recognized tribes Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Complete
4.13 | Adult Day Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 | 2018-11-29 | 2018-11-29 | 2018-11-29 | Complete
4.14 | EOHHS Task Force Meeting | Update, if asked | 4 | Brenna |  |  | 2018-11-09 |  | 2018-11-26 | 2018-11-26 | Complete
4.15 | Home Care Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-05 | 2018-12-05 | Complete
4.16 | DEA Providers Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Complete
4.17 | Senior Centers Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 | 2018-12-13 | 2018-12-13 |  | Complete
4.18 | Nursing Homes Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 | 2018-12-05 | 2018-12-05 | 2018-12-05 | Complete
4.19 | FQHCs Meeting | Transition update | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Complete
4.2 | Children’s Services Providers Meeting | MTM Meet-and-Greet/Overview | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Complete
4.21 | Hospitals/HARI Meeting | MTM Meet-and-Greet/Overview | 4 | Mike C. | Brenna Diana |  | 2018-11-09 |  | 2018-12-15 |  | Complete
4.22 | Long-Term Care Coordinating Council (LTCCC) Meeting | Transition Update | 4 | Mario, Marlanea | Brenna Diana |  | 2018-11-09 |  | 2018-12-12 |  | Complete
4.23 | EOHHS Task Force Meeting | Transition Update | 4 | Marlanea | Brenna Diana |  | 2018-11-09 |  | 2018-12-17 |  | Complete
4.24 | Managed Care Organizations & Dental Meeting | Update, as needed | 4 | January and Kristin |  |  | 2018-11-09 |  | 2018-11-27 |  | Complete
4.25 | MTM Town Hall Meeting | General Information (MTM) | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Complete
4.26 | Meeting with All Other Providers (Waiver Group)/Personal Choice/Care Mgmt |  | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Complete
4.27 | DXC Listservs Meeting |  | 4 | Brenna | Diana |  | 2018-11-09 |  | 2018-12-15 |  | Complete
4.28 | Long-Term Care Coordinating Council (LTCCC) Meeting | Transition Update | 4 | Brenna | Diana |  | 2018-11-09 |  | 2019-01-09 |  | Complete
4.29 | EOHHS Task Force Meeting | Transition Update | 4 | Marlanea | Brenna Diana |  | 2018-11-09 |  | 2019-01-28 |  | Complete
4.3 | SUMHLC Provider meeting | Outreach | 4 | Jason | Brenna Diana |  | 2018-11-20 | 2018-12-03 | 2018-12-03 | 2018-12-03 | Complete
4.31 | VA Meeting | Outreach | 4 | Mario | Diana |  | 2018-11-28 | 2018-12-10 | 2018-12-10 | 2018-12-10 | Complete
4.32 | Resident Service Coordinators meeting | Outreach | 4 | Jason | Brenna Diana |  |  |  | 2018-12-15 |  | Complete
4.5 | Draft and send targeted member letter to exiting users in Medicaid and ETP Programs | Communication | 4 | Brenna | Diana Meghan/Ave Legal |  | 2018-12-03 | 2018-12-03 | 2018-12-07 |  | Complete
4.51 | Create FAQ for List of outstanding provider questions around operational concerns. |  | 4 | Marlanea |  |  | 2018-12-11 | 2018-12-11 | 2018-12-31 |  | Complete
5.01 | Receive Performance Bond |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 | 2018-11-20 | Complete
5.02 | Receive Broker Professional Liability Insurance |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 | 2018-11-20 | Complete
5.03 | Receive Broker Workers' Compensation insurance |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 | 2018-11-20 | Complete
5.04 | Receive Broker automobile Liability |  | 5 | Purchasing | Mario |  | 2018-09-26 | 2018-08-16 | 2018-08-16 | 2018-11-20 | Complete | 11/28 Steve following up with Nicole to get an ETA, currently not prioritized with Bridges, January emailed Nicole to prioritize request
5.05 | Staffing Implementation Plan |  | 5 |  |  |  | 2018-09-26 | 2018-09-30 | 2018-10-15 | 2018-09-30 | Complete | Mario to email Kim Rauch to get member and household members file by 12/4
5.06 | Identify office location | Ensure the location complies with contract requirements | 5 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-01 | 2018-11-20 | Complete
5.07 | Ensure broker is licensed in RI | Contract Compliance | 5 | Jason | Mario |  | 2018-09-01 | 2018-11-01 | 2018-11-01 | 2018-11-20 | Complete
5.08 | Ensure broker is registered as a state vendor | Contract Compliance | 5 | Jason | Mario |  | 2018-09-01 | 2018-11-01 | 2018-11-01 | 2018-11-20 | Complete
5.09 | Review and approve key management positions to be located in RI | Contract Compliance | 5 | Jason | Mario |  | 2018-08-09 | 2018-09-30 | 2018-11-01 | 2018-09-30 | Complete
5.11 | Ensure RI operation is fully staffed (written attestation) | Contract Compliance | 5 | Jason | Ave Meghan |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-25 | Complete
5.12 | Receive Broker certification of truthfulness |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete
5.13 | Receive Broker certification of Legality |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete
5.14 | Receive Broker insurance endorsement |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete
5.15 | Receive Broker Comprehensive Liability Insurance |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete
5.16 | Receive Broker Property Damage Insurance |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete
5.17 | Receive Broker Errors and Omissions insurance |  | 5 | Jason | Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete
5.18 | Ensure Broker's ability to maintain confidential information (written attestation) |  | 5 | Jason | Ave |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-26 | Complete
5.19 | Broker's disclosure of ownership and control interest |  | 5 | Jason | Ave Mario |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-20 | Complete
5.22 | Broker's Ombudsman to be located in Rhode Island by end of 2019 Q1 | Staffing | 5 | Jason | Ave Mario |  | 2018-11-09 | 2018-11-09 | 2019-03-31 | 2018-11-28 | Complete
5.23 | MTM to consider employing from RI Works, RI Unemployment, M/WBE (P&P) | Staffing | 5 | Jason | Mario |  | 2018-09-26 | 2018-11-21 | 2018-11-28 | 2018-11-20 | Complete
5.24 | Ensure Broker's ability to maintain records for 10 years (written attestation) |  | 5 | Jason | Ave |  | 2018-09-26 | 2018-12-01 | 2018-12-07 | 2018-11-26 | Complete
5.26 | Review and approve Implementation Plan | Operations/transition | 5 | Jason | Mario |  | 2018-09-26 | 2018-10-15 | 2018-11-01 | 2018-01-20 | Complete
6.01 | EOHHS Meeting with RIPTA | Bus Pass technology | 6 | Jason | January Kristin |  | 2018-11-08 |  | 2018-11-14 | 2018-11-20 | Complete
6.02 | Review and approve MTM Website | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Complete
6.03 | Transfer of toll-free number(s) from LGTC to MTM or acquire new numbers | Operations | 6 | Marlanea | Jason |  | 2018-09-26 | 2018-11-16 | 2018-11-21 | 2018-11-27 | Complete
6.04 | Review and approve Mobile Apps (written attestation) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-01 | 2018-12-07 |  | Complete
6.05 | Ensure availability of Telephone Device for the Deaf (TDD) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-15 | 2018-12-18 | 2018-11-27 | Complete
6.06 | Ensure Automatic call distributor (ACD) is operational (written attestation) including call flow routing, call tracking and call extraction and reporting | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-15 | 2018-12-18 |  | Complete
6.07 | Verify that telephone backup system is operational (written attestation) | Operations | 6 | Mario | Jason |  | 2018-09-26 | 2018-12-15 | 2018-12-18 |  | Complete
6.08 | EOHHS to provide contact information and ensure connection between MTM and MCOs for coordination of services with MCOs | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-20 | Complete
6.09 | EOHHS to provide contact information and ensure connection between MTM and AEs for coordination of services with Coordination of services with AEs | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-27 | Complete
6.1 | EOHHS to provide contact information and ensure connection between MTM and RIPTA for coordination of services with RIPTA's RIde Program | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-20 | Complete
6.1 | RIPTA and MTM Meeting | Bus Pass distribution | 6 | Jason | Mario |  |  | 2018-11-21 | 2018-11-28 | 2018-11-28 | Complete
6.11 | EOHHS to provide contact information and ensure connection between MTM and high-utilizing providers for coordination of services with high-utilizing providers (Adult day, Dialysis, SUD, etc.) | Stakeholder engagement | 6 | Jason | Mario |  | 2018-09-26 | 2018-11-01 | 2018-11-07 | 2018-11-28 | Complete
6.12 | Review and approve proposed vehicle placard |  | 6 | Jason | Mario Meghan |  | 2018-11-28 | 2018-11-28 | 2018-12-07 |  | Complete
6.13 | Review and approve proposed driver ID badges |  | 6 | Jason | Mario Meghan |  | 2018-11-28 | 2018-11-28 | 2018-12-07 |  | Complete
6.15 | Finalize bus pass distribution process |  | 6 | Jason | Mario |  |  | 2018-11-15 | 2018-11-28 | 2018-11-29 | Complete
6.16 | State participation in call overflow, RHO call center (provider outreach LON and Standing orders) | Operations | 6 | Marlanea | Mark Lani |  | 2018-11-30 | 2018-11-30 | 2018-12-07 |  | Complete
6.17 | Address provider questions (Adult Day) |  | 6 | Jason | Diana Maria |  | 2018-11-29 | 2018-11-30 | 2018-12-08 |  | Complete
6.18 | Approve LGTC phone recording for 1/1 |  | 6 | Jason |  |  | 2018-11-20 |  | 2018-11-30 | 2018-11-30 | Complete
6.2 | Respond to request for grace period for post-trip verification requirements | Broker Requirements | 6 | Jason | Kristin | Ops Meeting | 2018-11-20 | 2018-11-21 | 2018-11-21 | 2018-11-26 | Complete
7.01 | Ensure pathway for assessing liquidated damages to Broker | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 | 2018-11-30 | Complete
7.02 | Ensure pathway to send capitation payments for Medicaid members to MTM | Finance | 7 | Marlanea | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 | 2018-11-27 | Complete
7.03 | Ensure pathway to send payments for the ETP program | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 | 2018-12-04 | Complete
7.04 | Ensure pathway to send payments for TANF program | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 |  | 2018-12-01 | 2018-12-04 | Complete
7.05 | Approve MTM financial reporting policy and templates | Finance | 7 | Mario | Kathy Corsino |  | 2018-09-26 | 2019-02-01 | 2019-02-10 |  | Complete
8.01 | Promulgation of Transportation Policy | State Policy | 8 | Tarah Provencal | Mario |  | 2018-09-26 | 2018-11-13 | 2018-12-31 |  | Complete
8.02 | CMS Approval of Transportation SPA | State Plan | 8 | Melody Lawrence | Mario |  | 2018-09-26 |  | 2018-12-31 | 2018-12-04 | Complete
6.17 | Update State Website to reflect MTM | Operations | 6 | Maria |  |  | 2018-12-12 | 2018-12-12 | 2018-12-31 |  | Complete
| Review updates to Opeational Policies from MTM | Operations | 6 | Mark |  |  | 2018-12-20 | 2018-12-20 | 2018-12-27 |  | Complete

## Risks & Issues
# | Risk / Issue | Origin | Date Created | Date Due | Description | Mitigation Plan | Primary Owner | Status | Notes
1.01 | Risk | 11/9 Internal Meeting | 2018-11-09 | 2018-11-16 | LGTC not providing member files | Acquire information from encounter data and facilities, open medical necessity for 3 or 6 months | Marlanea | Resolved | Marlanea is lead in systems
1.02 | Risk |  | 2018-11-09 | 2018-11-20 | Transition of toll free number from LGTC | MTM to acquire new toll free number | Marlanea | Resolved
2.01 | Risk |  | 2018-11-30 |  | RI NEMT TPs - pushing back on contracting with MTM - can result in inadequate TP network | MTM suggests contracting with RIPTA 12/4 MTM/RI NEMT and EOHHS met and are followint up 12/5 re: possible MOU to satisfy both parties | Mario | Resolved | 97 Executed contracts, potential RIPTA contract as well.

## Questions & Decisions
# | Question / Decision | Origin | Date Created | Date Due | Description | Outcome | Primary Owner | Status | Notes
1 | Question | 11/8 MTM Meeting | 2018-11-08 | 2018-11-30 | 10% pre and post verification partnering with EOHHS - what is the timeline for post-trip verification - change the percentage | 90 post implementation review |  | Resolved | 10% would take 4 full-time positions, can we decrease the percentage or give encounter data to MTM to use for trip verification
4.01 | Decision |  |  | 2018-12-03 | Decision on mailing the postcard as is or amending. Do we want to create a separate mailing? | Create 2 separate mailings |  | Resolved

## Project Metrics (hidden)
Metric # | Metric | Definition | Data Source | Person Responsible | Target Value | Target Goal | Target Date | Frequency | 2018-09-16 | 2018-09-23 | 2018-09-30 | 2018-10-07 | 10/14/2018 | 10/21/2018 | 10/28/2018 | 11/4/2018
1 | # of Overdue Applications in State Hands | # of applications pending after receipt from client that are workable by the State for more than 90 days | RIB Tableau KPI | XYZ |  |  |  | Weekly

## Data Validation (hidden)
Status | Project Manager | AI Status | QRID Status | Frequency | Agency | Decision Rights | Anticipated vs. Actual Completed by Today's Date
On Track | Jasper Frank | Blocked | Blocked | Daily | BHDDH | Approval Required | Start Date: | 2018-08-01
At Risk | Catherine Gering | Complete | In Progress | Weekly | DCYF | Consulted | Today's Date: | 2019-02-26
Off Track | Matt Kiehnle | In Progress | Not Yet Due | Monthly | Deloitte | N/A | End Date: | 2018-12-31
Other | Maria Narishkin | Incomplete | Overdue | Quarterly | DHS |  |  | Anticipated | Actual
|  | Not Yet Due | Resolved |  | EOHHS |  | Complete | 133 | 94
|  | Overdue | Unknown |  | HSRI |  | Incomplete | 6 | 45
|  | Unknown | Unresolved |  | Medicaid |  |  | 95.68% | 67.63%
|  | With Vendor | With Vendor |  | Other
|  | Critical |  |  | RIDOH
|  | Total | Total
|  | Complete | Resolved |  |  |  | Total Tasks | 139
|  | In Progress | In Progress
|  | Not Yet Due | Not Yet Due
|  | Unknown | Unknown
|  | Blocked | Blocked
|  | Incomplete | Unresolved
|  | Overdue | Overdue
Risks
Issues
Questions
Decisions