## Document Review
| Document Name | Date due to EOHHS | Date Provided by MTM | Date Reviewed By EOHHS | Reviewed By | Approved? | Date Sent back to MTM | Date Updated Document Received | Date Reviewed | Reviewed By | Approved ? | Notes
1 | ACA Language Insert | 2018-11-01 |  |  | Jason | No | 2018-11-16 |  |  |  | Yes | They should be using the state template
2 | Ambulance provider handbook |  | 2018-10-11 | 2018-10-26 | Mario and Jason | Yes
3 | Audit Recoupment Letter |  |  |  | Jason and Mario | Yes
4 | Authorization for transportation request form |  |  |  | Jason and Mario | Yes
5 | Bus Letter |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19 | 2018-11-19 | 2018-11-20 | Meghan | Yes
6 | CC urgent request guidelines |  |  |  | Jason and Mario | Yes
7 | Communication and education plan | [7 empty] | 2019-12-13 |  | Yes
8 | Complaint resolution letter |  |  | 2018-11-20 | Meghan | No | 2018-11-20 |  | 2019-12-13 |  | Yes
9 | Compliance plan | 2018-11-01 |  |  | Jason and Mario | Yes | [5 empty] | Provided 2018 Compliance Plan
10 | Daily pre-trip inspection report | 2018-11-01 |  |  | Jason and Mario | Yes
11 | Disaster Recovery |  | 2018-11-19 | 2018-11-19 | Ave | Yes | [5 empty] | Sent in lieu of staffing plan
12 | Distance verification form |  |  |  | Jason and Mario | Yes | 2018-11-20
13 | Facility Implementation Spreadsheet |  |  |  | Jason and Mario | No |  | 2018-11-20 |  | Jason | Yes
14 | Facility intro letter |  |  |  | Jason and Mario | No |  | 2018-11-20 |  | Jason | Yes
15 | FWA Integrity Plan | 2018-11-21 |  |  | Tom Bouchard | Yes
16 | Generic RFI |  |  |  | Jason and Mario | Yes
17 | GMR Trip Log doc |  |  |  | Jason and Mario | Yes
18 | Implementation | 2018-10-15 | 2018-09-01 |  | Jason and Mario | yes
19 | Language Attestation | 2018-12-15 |  |  | Jason and Mario | Yes |  | 2018-11-30 | 2018-11-30 | meghan | Yes
20 | Level of Need - Ambulance |  |  |  | Jason and Mario | Yes
21 | Level of Need - Standard |  |  |  | Jason and Mario | Yes
22 | Member behavior - action taken |  |  |  | Jason | No | 2018-11-16 |  | 2019-12-13 |  | Yes
23 | Member behavior - education letter |  |  |  | Jason | No | 2018-11-16 |  | 2019-12-13 |  | Yes
24 | Member behavior - warning letter |  |  |  | Jason | No | 2018-11-21
25 | MTM Currency Welcome Letter - no public transit (GMR Letter) |  | 2018-11-19 | 2018-11-19 | Meghan | No | 2018-11-19 | 2018-11-19 | 2018-11-20 | Meghan | Yes
26 | MTM Incoming call guide |  |  |  | Jason and Mario | Yes
27 | MTM overview PP |  |  |  | Jason | No | 2018-11-16 | 2018-11-21 |  | Jason | Yes | Sent back to EOHHS again
28 | MTM Protocols |  |  |  | Jason | Yes
29 | MTM Provider Audit
30 | No Show letter level 2 |  |  |  | Meghan/Jason | Yes
31 | No show letter level 3 |  |  |  | Meghan | No | 2018-11-20
32 | Policy 2001 New hire orientation |  | 2018-11-20 |  | Ave | Yes
33 | Policy 413 Management of No Shows |  | 2018-11-28 |  | Meghan | no
34 | Policy 435 Compliance and ethics |  | 2018-11-20 |  | Ave | Yes
35 | Policy 437 Compliance and ethics education training/outreach |  | 2018-11-20 |  | Meghan | Yes
36 | Policy 702 Annual compliance training |  | 2018-11-20 |  | Ave | Yes | [5 empty] | Submitted with Contract
37 | Policy 753 Documentation of ongoing training |  | 2018-11-20 |  | Ave | Yes
38 | Policy 9902 Regulatory Compliance |  | 2018-11-20 |  | Ave | Yes
39 | Postcard Text | 2018-11-01 |  |  | Meghan | No | 2018-11-21 | 2018-11-29 | 2018-11-30 | Meghan | Yes
40 | Procedue 602.007 Pre and post validation |  | 2018-11-20 |  | Ave | Yes
41 | Procedure 606.001 Claims web application-verification of claims |  | 2018-11-20 |  | Ave | Yes
42 | Procedure 700.002 sanction check search process |  | 2018-11-20 |  | Meghan | Yes
43 | Provider Handbook | 2018-11-21 |  |  | Meghan | Yes
44 | Quality Assurance Program | 12/1/2018 |  |  | Jason and Mario | Yes
45 | REPORT - Accident/incident client report |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
46 | REPORT - Claims timeliness report |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
47 | REPORT - Contact Center report - Call Queue |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
48 | REPORT - Contact Center report - Call stats |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
49 | REPORT - Monthly client summary report |  |  |  | Meghan |  |  |  | 2018-12-10 | Jason/Meghan | Yes
50 | REPORT - Monthly complaint report |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
51 | REPORT - RI dashboard |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
52 | REPORT - Sample Denial Detail Report |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
53 | REPORT - Sample FWA report |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
54 | REPORT - Sample Plan Detail Month Year |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
55 | REPORT - Sample pre/post dashboard |  | 2018-11-02 | [5 empty] | 2018-12-10 | Jason/Meghan | Yes
56 | REPORT - TP Monthly Report Card | [7 empty] | 2018-12-10 | Jason/Meghan | Yes
57 | REPORT - Trip detail report | [7 empty] | 2018-12-10 | Jason/Meghan | Yes
58 | RI Operating procedures manual | 2018-11-21 | 2018-11-20 | [5 empty] | 2018-12-25 | Jason/Meghan | Yes | See Ops Manual tab for checklist of P&Ps
59 | RI Works document
60 | Staffing plan | 2018-11-01 | 2018-09-25 |  | Contract review | Yes | [5 empty] | Submitted with Contract
61 | State Denial Letter |  | 2018-11-09 |  | Meghan | No | [5 empty] | Edits sent to Jason
62 | State resource guide |  | 2018-11-20 |  | Jason | No | 2018-11-21
63 | Town hall sign-in |  |  |  | Comm. Team |  |  |  | 2019-11-02 |  | Yes
64 | TP Contract Appendix A
65 | TP Contract Appendix B | 2018-11-15 | 2018-11-12 |  | Jason and Mario | Yes
66 | TP Contract Appendix C | 2018-11-15 | 2018-11-12 |  | Jason and Mario | Yes
67 | TP Contract Schedule A | 2018-11-15 | 2018-11-12 |  | Jason and Mario | Yes
68 | TP Contract Schedule B | 2018-11-15 | 2018-11-12 |  | Jason and Mario | Yes
69 | TP Contract TPSA
70 | TP Helpdesk |  | 2018-11-12 |  | Jason and Mario | Yes
71 | TP Training Ambulance community user credentialing reference guide |  | 2018-11-02 |  | Meghan | Yes
72 | TP Training Ambulance provider reference guide |  | 2018-11-02 |  | Meghan | Yes
73 | TP Training Appeals reference guide |  | 2018-11-02 |  | Meghan | Yes
74 | TP Training Claims reference guide |  | 2018-11-02 |  | Meghan | Yes
75 | TP Training Community User Credentialing PP |  | 2018-11-02 |  | Meghan | Yes
76 | TP Training Community User Credentialing reference guide |  | 2018-11-02 |  | Meghan | Yes
77 | TP Training Cultural Competency PP |  | 2018-11-02 |  | Ave | Yes | [5 empty] | Where are these docs, not detailed in Provider Handbook
78 | TP Training Denial reasons Claims FAQ |  | 2018-11-02 |  | Meghan | Yes
79 | TP Training ETD reference Guide |  | 2018-11-02 |  | Meghan | Yes
80 | TP Training New provider Training and nesting | 2018-11-01 | 2018-10-30 |  | Meghan | Yes
81 | TP Training Provider Trip management reference guide |  | 2018-11-02 |  | Meghan | Yes
82 | TP Training PTM and ETP PP |  | 2018-11-02 |  | Meghan | Yes
83 | TP Training Reveal driver app reference guide |  | 2018-11-02
84 | TP Training Reveal driver app training PP |  | 2018-11-02
85 | TP Training Reveal Provider portal PP |  | 2018-11-02
86 | TP Training Reveal proviider portal reference guide |  | 2018-11-02
87 | TP Training TP Compliance Training PP |  | 2018-11-02 | 2018-11-26 | Ave | [6 empty] | Where are these docs
88 | Vehicle Inspection and guidelines | 2018-11-01 |  |  | Jason and Mario | Yes
89 | Vehicle inspection form | 2018-11-01 |  |  | Jason and Mario | Yes
90 | VOC Presentation | 2018-11-01 |  | 2018-11-19 | Jason and Mario | No | 2018-11-21 |  |  |  |  | Provided in outreach plan
91 | Website Text |  |  | 2018-11-20 | Meghan | No | 2018-11-21 |  | 2019-12-10 | Jason | Yes

## Ops Manual
Item # | Policy or process | Date due to EOHHS | Date Provided by MTM | Date Reviewed By EOHHS | Reviewed By | Approved? | Date Sent back to MTM | Date Updated Document Received | Date Reviewed | Reviewed By | Approved ? | Notes
1 | Accident/incident escalation process
2 | Alternative transportation options
3 | Ambulance Contracting
4 | Attendent/escort policy
5 | Authorizing and scheduling services
6 | Breach of confidentiality process |  |  | 2018-11-26 | Ave | Yes
7 | Bus Route entry
8 | Bus Route fare inventory
9 | Call center service disruption |  |  | 2018-11-23 | Meghan | Yes
10 | Call monitoring/evaluation |  |  | 2018-11-23 | Meghan | Yes
11 | CCR response standards
12 | Challenging member policy
13 | Client audit management |  |  | 2018-11-23 | Meghan | Yes
14 | Complaint resolution policy |  |  | 2018-11-23 | Meghan | Yes |  |  | 2018-11-23 | Meghan | yes
15 | Compliance hotline |  |  | 2018-11-26 | Ave | No |  |  |  | Ave | No | Section #3, what is the significance of KPI as it relates to Hotline
16 | Cust serv cntr interaction conduct |  |  | 2018-11-23 | Meghan | Yes
17 | Denial of service letter |  |  | 2018-11-23 | Meghan | No |  |  | 2018-11-28 | Meghan | No
18 | Document retention |  |  | 2018-11-26 | Ave | Yes
19 | Eligibility verification process
20 | Emergency situations |  |  |  | Meghan |  |  |  | 2018-12-05 | Meghan | Yes
21 | Expedited resolutions of appeals process | [10 empty] | Only talks of expedited appeals related to provider payment in the provider manual
22 | Field Liaisons
23 | Financial Incentives |  |  |  | X
24 | FWA Prevention/investigation |  |  | 2018-11-23 | Meghan | No
25 | Grievance process policy |  |  | 2018-11-23 | Meghan | No |  |  | 2018-11-23 | Meghan | No
26 | Health Literacy |  |  | 2018-11-26 | Ave | No |  |  | 2018-11-27 | Ave | No
27 | HIPAA Member request compliance |  |  | 2018-11-26 | Ave | yes
28 | Hours of service 365/24/7
29 | Inclement Weather/traffic situations |  |  | 2018-12-05 | Meghan | Yes
30 | Interaction Handling |  |  | 2018-11-23 | Meghan | No
31 | Levels of service - Curb to curb
32 | Levels of service - Door to door
33 | Management of No shows |  |  |  | Meghan | No |  |  | 2018-11-28 | Meghan | No | just one edit
34 | Marketing Communications |  |  | 2018-11-26 | Ave | No |  |  | 2018-11-27 | Ave | No | need specificity around LEP, alternative formats, prior approval by state process for member communications Health Literacy should be a comp[anion doc to Marketing Communication
35 | Member eligibility |  |  |  | Meghan
36 | Modes of service - Ambulance (ALS/BLS)
37 | Modes of service - Mileage Reimbursement
38 | Modes of service - Multi-Passenger Van
39 | Modes of service - Public Motor Vehicle
40 | Modes of service - Public Transit
41 | Modes of service - Ride Share (Lyft)
42 | Modes of service - Stretcher Van
43 | Modes of service - Volunteer Drivers
44 | Modes of service - Wheelchair Van
45 | Month-end bus reconciliation
46 | MTM Satisfaction survey | [7 empty] | 2018-11-28 | Meghan | yes
47 | Office staff and CCR personnel P&P
48 | Payment process for TPs
49 | Peak transportation contingency plan
50 | Performance improvement plan administration
51 | Performance improvement plan, TP |  |  | 2018-11-26 | Ave | No |  |  |  | Ave | No | needs detail when state is notified and time frames
52 | Post authorization trips | [7 empty] | 2018-12-05 | Meghan | Yes
53 | Power outage system failure |  |  |  | Meghan
54 | Pre and Post Trip Verification P&P
55 | Process for short notice trip requests
56 | Process for TP trip assignment
57 | Provider audit and vehicle inspection
58 | Publication of members' rights |  |  | 2018-11-23 | Meghan | No
59 | Quality & Compliance committee/board |  |  | 2018-11-26 | Ave | No |  |  |  | Ave | No | Title does not reflect content; numbering under Responsibility begins w/#5; where is 1-4,Please review this P&P as it appears there are 2 policies here
60 | Re-credentialing Process |  |  | 2018-11-23 | Meghan | No |  |  |  |  | Yes | One Edit
61 | Recurring appointments |  |  |  | Meghan
62 | Relaying TP Issues | [7 empty] | 2018-12-05 | Meghan | Yes
63 | Reloadable public transit fare |  |  |  | X
64 | Reporting/handling accidents/incidents
65 | Special Needs transporation scheduling |  |  |  | Meghan
66 | Staff training curriculum (not TPs) including mode of transport determination, cultural |  |  | 2018-11-23 | Meghan | Yes
67 | TP Contracting
68 | TP Credentialing including list of excluded individuals |  |  | 2018-11-23 | Meghan | Yes
69 | TP Help Desk | [7 empty] | 2018-12-05 | Meghan | Yes
70 | TP Incentive program
71 | TP Monitoring, corrective action, termination |  |  | 2018-11-23 | Meghan | No | [5 empty] | One Edit
72 | TP Selection criteria
73 | TP Training including CPR, HIPAA, Cultural, Defensive driver
74 | Translation services |  |  | 2018-11-26 | Ave | No |  |  | 2018-11-27 | Ave | no | need detail re: notifying TPs
75 | Trip Recovery policy
76 | Utilization review policy